## Sheet1
Issue # | Description | Bug or Improvement | Functional Area(s) | Rel 2 | Rel 3 | Rel TBD
371 | Hitting Cancel while editing a document takes you to Urgent Notices management | BUG | Admin |  |  | x
364 | WYSIWYG Editor needs to allow embedded links to documents, folders, external sites | IMP. | Admin | x
363 | WYSIWYG Editor needs to facilitate embedded images | IMP. | Admin | x
362 | Newly created subfolder should be selected by default | IMP. | Admin: Library |  |  | x
361 | Ability to copy folder structures | IMP. | Admin: Library |  | x
360 | Add User-Managed Alert Types | IMP. | Admin: Alerts
359 | Standardize Type Editor | IMP. | Admin: Global |  | x
358 | Colour Selectors for Event/Communication Types | IMP. | Admin: Communications, Admin: Events |  |  | x
356 | Communication Types should be editable | IMP. | Admin: Communications |  | x
355 | Attach document(s) to Events | IMP. | Front-End |  | x
354 | Attach document(s) to Events | IMP. | Admin: Events | x
353 | Document Upload - Enhancements | IMP. | Admin: Library | x
352 | Cancel Alerts Confirmation Modals - Copy Updates | IMP. | Admin: Alerts |  |  | x
344 | Manage Alerts - Column sort indicators missing | BUG | Admin: Alerts |  | x
343 | Communications - Minor Improvements | IMP. | Admin: Comms |  |  | x
342 | Communications - New/Edit - a few bugs | BUG | Admin: Comms |  |  | x
340 | Create Quicklink - Canceling a type selection shouldn't leave the selector active | BUG | Admin: Dashboard |  |  | x
339 | Events Listing - HTML tags shouldn't be displayed | BUG | Admin: Events | x
336 | Missing back button/link (UX) | IMP. | Admin: Global |  | x
335 | Column sort: various issues/inconsistencies | BUG | Admin: Global |  | x
334 | Manage Alerts - No headers when no alerts | IMP. | Admin: Alerts |  |  | x
330 | Mutually exclusive store-selection (All vs. select) | BUG | Admin: Global |  | x
302 | Delay when saving events | BUG | Admin: Events | x
300 | Add Site management (MBR as use-case) | IMP. | Admin: Features |  | x
290 | Store-specific events | IMP. | Admin: Events
283 | Short-term Search Enhancements | IMP. | Front-End | x
276 | Deleting Quicklink-associated document should kill Quicklink | BUG | Admin: Dashboard | x
275 | Front-End Event-type filter on Calendar | IMP. | Front-End |  |  | x
273 | Move function for documents | IMP. | Admin: Library |  |  | x
253 | Responsive Breakpoints (tablets, back office screens) | IMP. | Front-End |  | x
245 | Reorder Packages | IMP. | Admin: Features, Admin: Packages | x
230 | Expanded Folder Tree on Landing | IMP. | Front-End
227 | Advanced Search | IMP. | Front-End |  |  | x
223 | Folder Tree navigation (separate expand vs. select) | IMP. | Admin: Global, Front-End |  |  | x
212 | View Links that are copy/paste-able | IMP. | Front-End |  |  | x
204 | View Images in a modal | IMP. | Admin: Global, Front-End |  |  | x
203 | Limit allowable file types | IMP. | Admin: Library |  |  | x
200 | Store Selection widget enhancements | IMP. | Admin: Global |  | x
194 | Document Upload - Review files - improvements | IMP. | Admin: Library | x
181 | Consistent form error messaging | IMP. | Admin: Global |  |  | x
180 | Manage Packages (UX) | IMP. | Admin: Packages |  |  | x
179 | Manage Features (UX) | IMP. | Admin: Features |  |  | x
177 | Dashboard - Two rows of selectable features | IMP. | Admin: Dashboard | x
176 | Branding - Background selection enhancements | IMP. | Admin: Dashboard |  |  | x