## Slide 1: ManagerWeb 1.0 Update February 5, 2016

## Slide 2: 1.0 Feature Set
Dashboard (Homepage)
Optional Left Navigation (added Jan. 2016)
Urgent Messaging (added Jan. 2016)
Security compliance (added Jan. 2016)
Document Library
  bona fide content management
  abandonment of rigid, pre-determined information hierarchy
Communications
  selected, regular communications transitioned from traditional email distribution
  persistent, accessible archive
Packages (Featured Content)
Calendar
Alerts

## Slide 3: Timelines

## Slide 4: Deliverables
Development
Release 1.0: Limited release
Release 1.1: First National release
Release 2.0+: Subsequent National releases
Content
Direct content population during limited release
Information Architecture (IA) and Taxonomy
Process outline
Training/Support
ManagerWeb feature overview/training
Content management best practices, workflow
One-on-one training and/or workshops
Documentation
Application documentation
Content delivery/management documentation
Requirements/Design/UX/UI/PM
Wireframes/Mockups, User Stories, Formal/Informal Requirements
Feedback/Survey/Focus Groups, Resource Coordination
Quality Assurance / UAT
Once-over of each release
UAT: Ops resources actually use the application and provide feedback

## Slide 5: Development Status
 | Total Tasks | Complete* | Review | Progressing | Pending
Count | 157 | 0 | 36 | 100 | 21
% | 100% | 0% | 23% | 64% | 13%
Priorities
Document Library
Alerts
Featured Content
Urgent Notice
 | Total Tasks | Complete* | Review | Progressing | Pending
Count | 149 | 0 | 37 | 93 | 19
% | 100% | 0% | 25% | 62% | 13%
Previous Update – Jan. 29
*Complete: No further development/adjustments
prior to demo/UAT