## Sheet1
Decide Checklist
Design Checklist - FGL/Mark's
Project Name: FGL Store Communications Web |  | Project Number: 8180
Project Manager: Daryl Suttie
The purpose of this checklist is to support project due diligence during the Design gate. Ensure the appropriate technology stakeholder teams are engaged. Review this checklist with your AVP to get signoff and upload it to Planview along with the updated PBP, CBA (if required) and TIA deliverables. These are mandatory for Deliver gate funding.
| Criteria | Comments
| Finance checklist reviewed and updated | • Review at Prep meeting with Accounting team (Excluding FGL) N/A
| If solution design or direction changes, ARB/ACT informed | • TIA may need to be revised and approval from ARB/ACT required
| Contractual commitment for funding reviewed with Vendor Management (if needed) | • Funding submission includes full contractual commitment (contract executed only with full dollar commitment and approval by ITPC/PIMC)
| Resource plan and conversations with resource teams/providers • Key resources secured for Deliver, Includes Demand Dashboard | • Identify required resources including delivery team, shared services, vendor, non-IT • If 3rd party required, discussions with Vendor Management
| Product backlog updated • Product Owner signoff gathered and recorded each sprint. Email/approval to be saved in project repository | • Identify and prioritize features • Update epics and user stories
| Risk assessment updated, tracking and monitoring continued | • Include at least 1 business representative (usually Product Owner) for assessment • Track and monitor risk throughout project
| Status reporting continued | • Status reporting for stakeholders
| Project planning continued • Delivery roadmap updated | • Included in ongoing status reporting
| Implementation plan drafted | • Enough detail to start Deliver
| Test strategy drafted • Quality Management team engaged and has reviewed | • Describe testing approach including various test types
| Transition plan started Service Level Requirements/Service Specification Information Document | • Refine service level and support model assumptions • Discussions with service management and potential sustaining teams itservicemanagement@fglsports.com
Comments:
Date: Feb 11/16
AVP Name: Micah Kalen
By checking this box, you are acknowledging this project will deliver the above-listed artifacts/activities in the Design gate.