## ManagerWeb Dev Tasks
Stretch | Functional Area | User | Development Task/Task Set | Type | Notes | Complete | Review | Progressing | Pending
| Core Navigation | Store | Banner Selection | Functional |  |  | X
| Core Navigation | Store | Banner Selection | Design/UX |  |  | X
| Core Navigation | Store | Left Navigation | Functional |  |  | x
| Core Navigation | Store | Left Navigation | Design/UX |  |  | x
x | Core Navigation | [code] | IP-based Store awareness | Functional |  |  |  |  | x
| Core Navigation | Store | Store selection | Functional |  |  | x
| Core Navigation | Store | Store selection | Design/UX |  |  | x
| Dashboard | Store | Layout - Background image | Design/UX |  |  | x
| Dashboard | Store | Featured Content | Design/UX |  |  |  | x
| Dashboard | Store | Featured Content | Functional | click to access |  | x
| Dashboard | Store | Quicklinks | Design/UX |  |  | x
| Dashboard | Store | Quicklinks | Functional |  |  | x
| Dashboard | Store | Communications feed | Design/UX |  |  | x
| Dashboard | Store | Latest Updates feed | Design/UX |  |  |  | x
| Dashboard | Store | Communications feed | Functional |  |  |  | x
| Dashboard | Store | Latest Updates feed | Functional |  |  |  | x
| Dashboard | Admin | Background image selection | Functional |  |  |  | x
| Dashboard | Admin | Background image selection | Design/UX |  |  |  | x
| Dashboard | Admin | Featured Content - Create | Functional | click to initiate |  |  | x
| Dashboard | Admin | Featured Content - Delete | Functional | click to initiate, confirm modal |  |  | x
| Dashboard | Admin | Featured Content - Create | Design/UX |  |  |  | x
| Dashboard | Admin | Featured Content - Delete | Design/UX |  |  |  | x
| Dashboard | Admin | Featured Content - Reorder | Functional |  |  |  | x
| Dashboard | Admin | Featured Content - Reorder | Design/UX |  |  |  | x
| Dashboard | Admin | Quicklinks - Add | Functional |  |  |  | x
| Dashboard | Admin | Quicklinks - Remove | Functional |  |  |  | x
| Dashboard | Admin | Quicklinks - Reorder | Functional |  |  |  | x
| Dashboard | Admin | Quicklinks - Add | Design/UX |  |  |  | x
| Dashboard | Admin | Quicklinks - Remove | Design/UX |  |  |  | x
| Dashboard | Admin | Quicklinks - Reorder | Design/UX |  |  |  | x
| Dashboard | Admin | Lastest Updates - date window config | Functional |  |  |  | x
| Dashboard | Admin | Latest Communications - date window config | Functional |  |  |  | x
| Dashboard | Admin | Lastest Updates - date window config | Design/UX |  |  |  | x
| Dashboard | Admin | Latest Communications - date window config | Design/UX |  |  |  | x
| Featured Content | Store | Layout - Background image | Design/UX |  |  |  | x
| Featured Content | Store | Top-level documents | Design/UX |  |  |  | x
| Featured Content | Store | Top-level folders | Design/UX |  |  |  | x
| Featured Content | Store | Latest Updates feed | Design/UX |  |  |  | x
| Featured Content | Store | Layout - Background image | Functional |  |  |  | x
| Featured Content | Store | Top-level documents | Functional |  |  |  | x
| Featured Content | Store | Top-level folder - selection | Functional | click to access |  |  | x
| Featured Content | Store | Latest Updates feed | Functional |  |  |  | x
| Featured Content | Store | Top-Level folder - landing | Design/UX |  |  |  | x
| Featured Content | Store | Folder detail - subfolder navigation/expansion | Design/UX |  |  |  | x
| Featured Content | Store | Folder detail - breadcrumbs | Design/UX |  |  |  | x
| Featured Content | Store | Folder detail - subfolder navigation/expansion | Functional |  |  |  | x
| Featured Content | Store | Folder detail - breadcrumbs | Functional |  |  |  | x
| Featured Content | Admin | Edit Title | Design/UX |  |  |  | x
| Featured Content | Admin | Add Tile Label | Design/UX |  |  |  | x
| Featured Content | Admin | Set Visibility | Design/UX |  |  |  | x
| Featured Content | Admin | Background image selection | Design/UX |  |  |  | x
| Featured Content | Admin | Top-level document - add/select | Design/UX |  |  |  | x
| Featured Content | Admin | Top-level document - remove | Design/UX |  |  |  | x
| Featured Content | Admin | Top-level documents - reorder | Design/UX |  |  |  | x
x | Featured Content | Admin | Latest Updates - date window config | Design/UX |  |  |  | x
| Featured Content | Admin | Edit Title | Functional |  |  |  | x
| Featured Content | Admin | Add Tile Label | Functional |  |  |  | x
| Featured Content | Admin | Set Visibility | Functional |  |  |  | x
| Featured Content | Admin | Background image selection | Functional |  |  |  | x
| Featured Content | Admin | Top-level document - add/select | Functional |  |  |  | x
| Featured Content | Admin | Top-level document - remove | Functional |  |  |  | x
| Featured Content | Admin | Top-level documents - reorder | Functional |  |  |  | x
x | Featured Content | Admin | Latest Updates - date window config | Functional |  |  |  | x
| Featured Content | Admin | Top-level folder - add | Design/UX |  |  |  | x
| Featured Content | Admin | Folder - add item | Design/UX |  |  |  | x
| Featured Content | Admin | Folder - add folder | Design/UX |  |  |  | x
| Featured Content | Admin | Folder - add folder set | Design/UX |  |  |  | x
| Featured Content | Admin | Folder - remove | Design/UX |  |  |  | x
| Featured Content | Admin | Folder item - remove | Design/UX |  |  |  | x
| Featured Content | Admin | Folder - remove folder set | Design/UX |  |  |  | x
| Featured Content | Admin | Top-level folder - add | Functional |  |  |  | x
| Featured Content | Admin | Folder - add item | Functional |  |  |  | x
| Featured Content | Admin | Folder - add folder | Functional |  |  |  | x
| Featured Content | Admin | Folder - add folder set | Functional |  |  |  | x
| Featured Content | Admin | Folder - remove | Functional |  |  |  | x
| Featured Content | Admin | Folder item - remove | Functional |  |  |  | x
| Featured Content | Admin | Folder - remove folder set | Functional |  |  |  | x
| Communications | Store | Communications listing | Design/UX |  |  |  | x
| Communications | Store | Communication detail | Design/UX |  |  |  | x
| Communications | Store | Communication detail - view attachment | Design/UX |  |  |  | x
| Communications | Store | Communications listing | Functional |  |  |  | x
| Communications | Store | Communication detail | Functional |  |  |  | x
| Communications | Store | Communication detail - view attachment | Functional |  |  |  | x
x | Communications | Store | Search | Design/UX |  |  |  |  | x
x | Communications | Store | Search Results | Design/UX |  |  |  |  | x
x | Communications | Store | Search | Functional |  |  |  |  | x
x | Communications | Store | Search Results | Functional |  |  |  |  | x
| Communications | Admin | Add Communication | Design/UX |  |  |  | x
| Communications | Admin | Remove Communication | Design/UX |  |  |  | x
| Communications | Admin | Edit Communication | Design/UX | form clean-up |  |  | x
| Communications | Admin | Edit Communication - Title | Design/UX |  |  |  | x
| Communications | Admin | Edit Communications - Set Visibility | Design/UX |  |  |  | x
| Communications | Admin | Edit Communications - WYSIWIG message | Design/UX |  |  |  | x
| Communications | Admin | Edit Communications - Attachment - Add | Design/UX |  |  |  | x
| Communications | Admin | Edit Communications - Attachment - Remove | Design/UX |  |  |  | x
x | Communications | Admin | Edit Communications - Tag | Design/UX |  |  |  | x
| Communications | Admin | Add Communication | Functional |  |  |  | x
| Communications | Admin | Remove Communication | Functional |  |  |  | x
| Communications | Admin | Edit Communication | Functional |  |  |  | x
| Communications | Admin | Edit Communication - Title | Functional |  |  |  | x
| Communications | Admin | Edit Communications - Set Visibility | Functional |  |  |  | x
| Communications | Admin | Edit Communications - WYSIWIG message | Functional |  |  |  | x
| Communications | Admin | Edit Communications - Attachment - Add | Functional |  |  |  | x
| Communications | Admin | Edit Communications - Attachment - Remove | Functional |  |  |  | x
x | Communications | Admin | Edit Communications - Tag | Functional |  |  |  | x
| Alerts | Store | Alert Listing | Design/UX |  |  |  | x
| Alerts | Store | Listing - Store Filter | Design/UX |  |  |  | x
| Alerts | Store | Alert Listing | Functional |  |  |  | x
| Alerts | Store | Listing - Store Filter | Functional |  |  |  | x
| Document Library | Store | Folder Traversal | Design/UX |  |  | x
| Document Library | Store | Search | Design/UX |  |  |  |  | x
| Document Library | Store | Search Results | Design/UX |  |  |  |  | x
| Document Library | Store | Folder Traversal | Functional |  |  | x
| Document Library | Store | Search | Design/UX |  |  |  |  | x
| Document Library | Store | Search Results | Functional |  |  |  |  | x
| Document Library | Store | Search | Functional |  |  |  |  | x
| Document Library | Store | Search Results | Functional |  |  |  |  | x
| Document Library | Admin | Add folder | Design/UX |  |  | x
| Document Library | Admin | Add subfolder | Design/UX |  |  | x
| Document Library | Admin | Upload document | Design/UX |  |  | X
| Document Library | Admin | Edit document (metadata) | Design/UX |  |  | X
| Document Library | Admin | Remove document | Design/UX |  |  | X
| Document Library | Admin | Remove folder | Design/UX |  |  | x
| Document Library | Admin | Remove folder with subfolders | Design/UX |  |  |  | x
| Document Library | Admin | Add folder | Functional |  |  | X
| Document Library | Admin | Add subfolder | Functional |  |  | X
| Document Library | Admin | Upload PDF | Functional |  |  | x
| Document Library | Admin | Upload image (JPG, GIF, PNG) | Functional |  |  | x
| Document Library | Admin | Upload MP4 | Functional |  |  | x
| Document Library | Admin | Edit document (metadata) | Functional |  |  | x
| Document Library | Admin | Remove document | Functional |  |  | x
| Document Library | Admin | Remove empty folder | Functional |  |  |  | x
| Document Library | Admin | Remove folder with subfolders or docs | Functional |  |  |  | x
| Document Library | [ code ] | Folder/document removal impacts to Featured Content | Functional |  |  | x
| Document Library | [ code ] | Folder/document removal impacts to Communications | Functional |  |  | x
| Documents | Store | View PDF | Design/UX |  |  | x
| Documents | Store | View Image (JPG, GIF, PNG) | Design/UX |  |  |  | x
| Documents | Store | View MP4 | Design/UX |  |  |  | x
| Documents | Store | Download XLS, XLSX | Design/UX |  |  |  | x
| Calendar | Store | View Calendar | Design/UX |  |  | x
| Calendar | Store | View Event Details | Design/UX |  |  | X
| Calendar | Store | Print | Design/UX |  |  |  |  | x
| Calendar | Store | View Calendar | Functional |  |  | x
| Calendar | Store | View Event Details | Functional |  |  |  | x
| Calendar | Store | Print | Functional |  |  |  |  | x
| Calendar | Admin | Create/Edit Event | Design/UX |  |  | X
| Calendar | Admin | Delete Event | Design/UX |  |  | x
| Calendar | Admin | Create/Edit Event | Functional |  |  | x
| Calendar | Admin | Delete Event | Functional |  |  | x
| Dashboard | Store | Display Urgent Update CTA/link | Design/UX |  |  |  |  | x
| Dashboard | Store | Display Urgent Update CTA/link | Functional |  |  |  |  | x
| Dashboard | Admin | Display Urgent Update CTA/link | Design/UX |  |  |  |  | x
| Dashboard | Admin | Display Urgent Update CTA/link | Functional |  |  |  |  | x
| Left Nav | Store | Left Navigation - optional components | Functional |  |  |  |  | x
| Left Nav | Store | Left Navigation - optional components | Design/UX |  |  |  |  | x
| Left Nav | Admin | Left Navigation - optional components | Functional |  |  |  |  | x
| Left Nav | Admin | Left Navigation - optional components | Design/UX |  |  |  |  | x

## Overview
| Dev Tasks | Complete | Review | Progressing | Pending
Count | 157 | 0 | 36 | 100 | 21
% | 100% | 0% | 22.93% | 63.69% | 13.38%