## Cycle 1 Tasks
Partial Shipment - Additional Scenarios
PSS-
Workgroup | Role | Day | Workflow/Scenario | Task Nbr | Task ID | Order | Pick Ticket | Task | Expected Results | Prerequisites/Notes | Assigned To | Role | Status | Comments
ECOMM QA | Customer | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Place the order as per spec | Order placed successfully |  |  | Customer | PASSED
Warehouse | Packing | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Short SKU 147020033990000 from the order (tax exempt) | Order modified in WM |  |  | Packer | NOT RUN
ECOMM QA | Packing | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Generate/review the revised packing slip | Modified packing slip matches what was packed | #REF! |  | Packer | NOT RUN
Warehouse | Packing | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Pack the order | Packs through with the modified quantities | #REF! |  | Packer | NOT RUN
Customer Service | Agent | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Review the order in the CS Cockpit | Partial shortage ticket created; consignment modified, order paid. |  |  | CS Agent | NOT RUN
Finance | Auditor | 2015-11-26 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Review the sale in AuditWorks | Sale transaction is accurate and balanced |  |  | Auditor | NOT RUN
Customer Service | Agent | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Initiate a full return of modified order | Return is initiated | #REF! |  | CS Agent | NOT RUN
Warehouse | Receiving | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Receive the return as per RMA | RMA is received | #REF! |  | Receiving | NOT RUN
Customer Service | Agent | 2015-11-25 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Review the return request in the CS Cockpit | RMA is processed; order is returned. | #REF! |  | CS Agent | NOT RUN
Finance | Auditor | 2015-11-26 | PSS-03-01 | #REF! | #REF! | 003070402 | E000903007 | Review the return in AuditWorks | Return transaction is accurate and balanced | #REF! |  | Auditor | NOT RUN
ECOMM QA | Customer | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Place the order as per spec | Order placed successfully |  |  | Customer | PASSED
Warehouse | Packing | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Short SKU 331007232 from the order (not tax exempt) | Order modified in WM |  |  | Packer | NOT RUN
ECOMM QA | Packing | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Generate/review the revised packing slip | Modified packing slip matches what was packed | 0 |  | Packer | NOT RUN
Warehouse | Packing | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Pack the order | Packs through with the modified quantities | #REF! |  | Packer | NOT RUN
Customer Service | Agent | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Review the order in the CS Cockpit | Partial shortage ticket created; consignment modified, order paid. |  |  | CS Agent | NOT RUN
Finance | Auditor | 2015-11-26 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Review the sale in AuditWorks | Sale transaction is accurate and balanced |  |  | Auditor | NOT RUN
Customer Service | Agent | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Initiate a full return of modified order | Return is initiated | #REF! |  | CS Agent | NOT RUN
Warehouse | Receiving | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Receive the return as per RMA | RMA is received | #REF! |  | Receiving | NOT RUN
Customer Service | Agent | 2015-11-25 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Review the return request in the CS Cockpit | RMA is processed; order is returned. | #REF! |  | CS Agent | NOT RUN
Finance | Auditor | 2015-11-26 | PSS-03-02 | #REF! | #REF! | 002994343 | E000903010 | Review the return in AuditWorks | Return transaction is accurate and balanced | #REF! |  | Auditor | NOT RUN